## Revision History
Revision History
Ver. No. | Ver. Date | Prepared By | Reviewed By | Review Date | Approved By | Affected Section & Summary of Change
1.0.1

## EPICUser Stories
EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE
Epic/ US # | LOE Hours | LOE Hours Notes | Business Value - High: Must-have Medium: Should-have Low: Nice-to-have | Stakeholder Group | Epic/ User Story | Title | As a(n) | <USER TYPE> | I want | <FUNCTION>/ <Business Need> | so that | <BENEFIT>/<Business Value> | Questions/Comments for NHTSA or Stakeholders | Acceptance Criteria 1 | Acceptance Criteria 2 | Acceptance Criteria 3
THEME: | HOSTING PLATFORM / SYSTEM INFRASTRUCTURE (NSTRC & DREData 2.0)
1 | 360 |  |  | NHTSA | EPIC | Hosting Platform | As a(n) | System Owner | I want | to move the on-premises production site into the cloud and host the NSTRC and DREData 2.0 systems in the cloud environment, utilize the cloud hosting platforms and services such as infrastructure as a service (IaaS) and platform as a service (PaaS) | so that | I no longer have to worry about security updates and other administrative tasks on the operating system and the middleware level.
2 |  | hours included in 1 |  | NHTSA | EPIC | NSTRC and DREData 2.0 Systems Infrastructure | As a(n) | System Owner | I want | to build the NSTRC and DREData 2.0 application on the Amazon Web Services (AWS) FedRAMP approved US East/West Infrastructure as a service (IaaS) offering In addition to the DREData 2.0 web application, the Infrastructure in AWS will support the creation of the National Sobriety Testing Resource Center (NSTRC) website. The NSTRC site will replace the current site, and will host static informational content. | so that | NHTSA can utilize such AWS cloud benefits like reduced costs, rapid deployment, greater innovation, increased flexibility and improved security.
THEME: | DATA MIGRATION
13 | 480 |  |  | NHTSA | EPIC | Data Migration to Cloud Database | As a(n) | System Owner | I want | to migrate all NSTRC/DRE legacy data into the new cloud database without any loss of integrity or business information | so that | we keep maintaining the data integrity, therefore the value of the application, and all legacy data will be retained for the users within the new application.
14 |  | included in 13 |  | NHTSA | EPIC | Data Integrity |  | System Owner | I want | reconcile missing or improperly formatted data from the old system with the new business rules (Required fields, date formats, different options selected) | so that | NHTSA will have a greater confidence in system reports and analytics, increased user satisfaction.
THEME: | SYSTEM SECURITY
15 | 0 | TBD |  | NHTSA | EPIC |  | As a(n) | System Owner | I want | to comply with NHTSA/DOT Security Policy (TBD) | so that | we keep maintaining the data integrity and therefore the value of the application | Need to get Security Policy requirements.
THEME: | NSTRC PUBLIC SITE
16 | 12 |  |  | NHTSA | EPIC | NSTRC - Public SIte | As a(n) | Sobriety System Owner | I want | to make NSTRC (National Sobriety Testing Resource Center) site a public site with the URL SobrietyTesting.NHTSA.gov | so that | Sobriety Testing Resources will be available to public.
17 |  | included in 16 |  | NHTSA | EPIC | NSTRC URL and No Login | As a(n) | Sobriety System Owner | I want | the NSTRC site to be a public site with no login required | so that | information can be seen by anyone who has access to the Internet, without being required to login.
THEME: | NSTRC PAGE ELEMENTS
21 |  | included in 3 |  | NHTSA | EPIC | NSTRC Major Page Elements | As a(n) | Sobriety System Owner | I want | each page to have the following major page elements: - Global Header - Main Page Content - Global Footer | so that | it will help to unify the site, provide easy access helpful links and information.
22 |  | included in 3 |  | NHTSA | EPIC | NSTRC Global Header | As a(n) | Sobriety System Owner | I want | the Global Header to include the following elements: - Site title with site logo (link to a Home page) - Primary navigation (Mega menus) | so that | it will be easy to identify Sobriety Center site and navigate using the global navigation menu and tags.
23 |  | included in 3 |  | NHTSA | EPIC | NSTRC Links to Local Directory Sites | As a(n) | Sobriety System Owner | I want | State Directory information section to be removed from the right rail of the current Sobriety Center site and instead, include links (anywhere on the page) to local sites that update State directory information regularly: www.decp.org; NHTSA.gov; NDAA.org | so that | users can easily locate State Coordinators. TSRPs (Traffic Safety Resource Prosecutor), SFST information, etc.
THEME: | NSTRC LANDING PAGE
28 |  | included in 21 |  | NHTSA | EPIC | NSTRC Landing Page | As a(n) | Sobriety System Owner | I want | landing page to provide the following content and functionality: - NHTSA-related most recent updates - NHTSA important links - Main tabs and respective content - Basic Search functionality (Google Search) | so that | public users will have a quick and easy access to most recent and important information posted on the website. | Same as 25
29 |  | included in 21 |  | NHTSA | EPIC | NSTRC Main Tabs/Pages | As a(n) | Sobriety System Owner | I want | to have the content (document links, video links, external web links) published on the following main Tabs: - Glossary - Library - Videos - Web Resources | so that | public users can easily understand how the NSTRC information is sectioned and grouped. | Same as 25
THEME: | NSTRC SEARCH
34 | 24 |  |  | NHTSA | EPIC | NSTRC - Google Search | As a(n) | Sobriety System Owner | I want | the Google Search functionality to: - be easy to use - have an ability to search for page text - help pubic users to find the correct documentation/reference links - display results in a meaningful way - provide search autocomplete options for user to select from (TBD) | so that | the information will be more accessible, the time it takes to locate desired information will be reduced by eliminating the need to find information manually, and by performing searches at high speeds, thereby making people more efficient users of the website.
35 |  | included in 34 |  | NHTSA | EPIC | NSTRC - Search by Title | As a(n) | Sobriety System Owner | I want | to keep the search functionality very simple (no advanced searching) - with two key elements on a search section: - a field to enter the search terms (with autocomplete search options) - a ‘search’ button | so that | it will be be clear, easy, and above all, simple to use.
|  | THEME: | DREData 2.0 INTERNAL SITE
38 | 12 |  |  | NHTSA | EPIC | DREData 2.0 - NHTSA Internal/Private site - URL | As a(n) | DRE System Owner | I want | DREData 2.0 (Drug Recognition Expert Data System) site to be a private site with its own URL (DREData.NHTSA.gov) | so that | it will require user credentials to access the site.
39 | 36 |  |  | NHTSA | EPIC | DREData 2.0 Login | As a(n) | DRE System Owner | I want | DREData 2.0 site to require user account | so that | DREData 2.0 site information is hidden from public viewing and available only to registered users.
40 | 1.5 |  |  | NHTSA | EPIC | Link to NSTRC site | As a(n) | DRE System Owner | I want | to display a global link to NSTRC Landing page on the DREData 2.0 site (to be opened in a new browser tab upon clicking on the link) | so that | DREs can have an easy access to NSTRC site while managing information on DREData 2.0 site.
THEME: | DREData 2.0 USER ROLES / PERMISSIONS / POLICIES
41 | 60 |  |  | NHTSA | EPIC | Role Based Access (DREData 2.0) | As a(n) | DRE System Owner | I want | users (people) to be assigned predefined roles (functions) with certain permissions (define what authorizations those functions have) with the ability to add additional policies to each role to expand permissions | so that | the system will have a clear separation of functionality for various users and improve website's security.
42 |  | included in 41 |  | NHTSA | EPIC | User Roles | As a(n) | DRE System Owner | I want | to have the following 7 user roles, with the ability to assign only one role for each user: 1. National Coordinator (NC) 2. NHTSA Regional Coordinator (NTRC) 3. State Coordinator (SC) 4. Regional Coordinator (RC) 5. Agency Coordinator (AC) 6. Drug Recognition Expert (DRE) 7. Basic User (BU) [breakdown by role: user who has this permission, can see everything on the system the same is with the edit permissions, can edit everything (and this task will be done page by page)] | so that | each user will have a certain predefined access to the system.
THEME: | DREData 2.0 LOGIN & SYSTEM ACCESS
47 |  | included in 48 |  | NHTSA | EPIC | DREData 2.0 Login & System Access | As a(n) | DRE System Owner | I want | to have an authorized access based on User ID (Email) and Password used to log into the system which is associated with the user roles/responsibilities | so that | DREData 2.0 application (which replaces the legacy application with an overall information system sensitivity categorization of Moderate) can utilize the same eAuthentication Level 2: Single factor remote authentication requirements as the legacy application.
THEME: | DREData 2.0 FUNCTIONALITY ACCESS
52 |  | included in 41 and 44 |  | NHTSA | EPIC | Functional Tabs | As a(n) | DRE System Owner | I want | the DREData 2.0 web application to have the following functional tabs (access to tabs very depending on access of the user logged): - DASHBOARD: --- [Based on Role] --- DRE --- DRE-INS - EVALUATIONS: --- ALL EVALUATIONS --- DELETE EVALUATIONS (TBD) --- NEW EVALUATION - REPORTS: --- ALL REPORTS --- AD-HOC REPORTS --- CANNED REPORTS | so that | they can successfully perform their NTRC's role day to day activities.
53 | 36 |  |  | NHTSA | EPIC | DRE-INS View | As a(n) | DRE System Owner | I want | 1. DRE-INS to have a default view of all Evaluations in "Submitted" status under his/her region, with the ability to see evaluations from all other regions under his/her State. 2. to Include "Show me all" button. 3. Ability to change default Region - TBD | so that | they can successfully perform their NTRC's role day to day activities. | Do we still need an ability to change the default Regions for DRE-INS, since we are going to have an ability to VIEW ALL under entire State?
THEME: | DREData 2.0 EVALUATION LIFECYCLE
54 | 36 |  |  | NHTSA | EPIC | Evaluation Lifecycle | As a(n) | System Owner | I want | each evaluation to go through a lifecycle with the following 6 main workflow steps: 1. DRE enters evaluation information into the evaluation 2. DRE adds evaluator's opinion, submits the record to DRE-INS for review and approval, and submits specimen to Lab 3. DRE-INS rejects/approves the evaluation record, DRE corrects/updates the evaluation record. DRE-INS approves it; 4. Toxicology results are ready; 5. DRE saves; 6. Evaluation is locked | so that | all evaluations are going through the same approval process where the records are passed from one participant to another for action, according to a set of procedural rules.
55 | 12 |  |  | NHTSA | EPIC | Evaluation Lock | As a(n) | System Owner | I want | - The evaluation and toxicology report will exist within the same form in the DREData 2.0 web application. - The evaluation to be editable by users with Create/Update permissions - The evaluation to become locked for all users once the opinion has been submitted - If the field ‘Will Toxicology Results be Available?’ (WTRA) Is marked ‘Yes, Test is Complete’ then the toxicology sections become editable | so that | the evaluation record can be properly managed.
THEME: | DREData 2.0 CHANGE / RESET MY PASSWORD
58 | 24 |  |  | NHTSA | EPIC | Change My Password Page | As a(n) | DRE System Owner | I want | the system display the Change Your Password page upon user's first login into the system with the following fields. elements: - Password Rules - Current Password (field) - New Password (field) - Confirm New Password (field) - Save Password (button) | so that | the user is forced to reset the temporary password.
59 |  | included in 48 |  | NHTSA | EPIC | Forgot My Password Link | As a(n) | DRE System Owner | I want | the system to provide the self service password reset link on the Login page (for users who forgot their passwords) | so that | all users have an ability to proactively and securely self reset / change login passwords with ease from the web page.
THEME: | DREData 2.0 PAGE ELEMENTS
65 | 60 |  |  | NHTSA | EPIC | DRE Major Page Elements | As a(n) | DRE System Owner | I want | build a site template where each page will have the following major page elements: - Global Header - Navigation tabs - Global Footer | so that | it will help to unify the site, provide easy access helpful links and information across entire site.
66 |  | included in 65 |  | NHTSA | EPIC | DRE Global Header | As a(n) | DRE System Owner | I want | the Global Header to include the following elements: - Site title with site logo (link to a Dashboard page) - Tab navigation (Mega menus) - Banner links | so that | it will be easy to identify DRE site and navigate using the global navigation menu and other header tools.
THEME: | DREData 2.0 DASHBOARD TAB INFORMATION AND FIELDS
72 | 36 |  |  | NHTSA | EPIC | Dashboard Sections (Coordinators) | As a(n) | NC/NTRC/SC/RC/AC /TL | I want | the DASHBOARD sections to displays the following information: - NC/NTRC/SC/RC/AC/TL Section [National/NHTSA Regional/State/Regional/Agency/State]: --- Open/Unfinished Evaluations [No opinion entered] --- Submitted Evaluations [submitted to DRE-INS but not approved yet] --- Rejected [by DRE-INS] --- Approved [by DRE-INS] --- Completed [Tox. entered, locked, a year from now] --- SEARCH - DRE Section [Own Level]: --- Open/Unfinished Evaluations [No opinion entered] --- Submitted Evaluations [submitted to DRE-INS but not approved yet] --- Rejected [by DRE-INS] --- Approved [by DRE-INS] --- Completed [Tox. entered, locked, a year from now] --- SEARCH - DRE-INS Section [National/NHTSA Regional/State Levels]: --- Evaluations Assigned to Me --- Evaluations I Rejected --- Evaluations I Approved --- SEARCH | so that | I can successfully perform my daily job duties.
73 |  | included in 72 |  | NHTSA | EPIC | Dashboard sub tabs (DRE) | As a(n) | DRE | I want | the DASHBOARD sub tabs to display the following information: - DRE Subtab [Own Level]: --- Open/Unfinished Evaluations [No opinion entered] --- Submitted Evaluations [submitted to DRE-INS but not approved yet] --- Rejected [by DRE-INS] --- Approved [by DRE-INS] --- Completed [Tox. entered, locked, a year from now] --- SEARCH - DRE-INS Subtab [National/NHTSA Regional/State Levels]: --- Evaluations Assigned to Me --- Evaluations I Rejected --- Evaluations I Approved --- SEARCH | so that | I can successfully perform my daily job duties.
THEME: | DREData 2.0 EVALUATION TAB INFORMATION AND FIELDS
76 | 12 |  |  | NHTSA | EPIC | Evaluations sub tabs | As a(n) | NC/NTRC/SC/RC/AC/TL/DRE | I want | the EVALUATIONS sub tabs to display the following information: - ALL EVALUATIONS Subtab [National Level] --- All Evaluations [list, year from now] - NEW EVALUATION [Own Level] --- Face Sheet Form with additional NHTSA fields | so that | I can successfully review all and enter my own evaluations.
THEME: | DREData 2.0 EVALUATION AUDITS
99 | 240 |  |  | NHTSA | EPIC | Audits on Evaluation Edits | As a(n) | NC/NTRC/SC/RC/AC | I want | DREData 2.0 to introduce Auditing to the Evaluation Sheet. Key aspects of this new feature to include: - Coordinators only able to run Audit Reports for Evaluations within their AoR. - Notification and Reporting thresholds can be set by each Coordinator for their own AoR --- Two thresholds to be available: Number of changes per evaluation and Time between Submission and Update -------- Default notification to be set at 3 changes per evaluation post submission ---------Default notification to be set at >= 2 weeks between submission and update - Notifications to be sent automatically to the Coordinators via email based on their set thresholds. The Notification to show the number of times the record was changed, and the name of the field that was changed. - Notification Example: Record was updated 2 times: Update 1 ‘Opinion’ and ‘Evaluation Type’ was changed, Update 2 ‘Last Name’ was changed - Audit Reports can also be run by Coordinators on an ad hoc basis from the Reporting Menu. The ad hoc report to be the same format as the Notification, but to be run against the entire AoR for a date range the Coordinator chooses. | so that | this auditing feature will allow coordinators to see how often a record is changed, what field was changed and who made the change.
THEME: | DREData 2.0 TOXICOLOGY REPORT FIELDS
100 | 36 |  |  | NHTSA | EPIC | Audits on Evaluation Edits | As a(n) | NC/NTRC/SC/RC/AC/TL/DRE | I want | within the evaluation record, if the field ‘Will Toxicology Results be Available?’ has the selection set to ‘Yes, Test is Complete’ then the Toxicology Results Section to become editable. Each of the multi select fields (drugs) to be self servicing by Admins. The fields within this section are: Toxicology Results: - Alcohol Found: (Check Box) ¦ BAC Found: Free Text - No Drugs Found: (Checkbox) - Toxicology results will not be available: (Checkbox) - Lab unable to test: (Checkbox) | so that | I can easily capture Lab toxicology results in the system.
101 | 12 |  |  | NHTSA | EPIC | Toxicology - Other 1 | As a(n) | NC/NTRC/SC/RC/AC/TL/DRE | I want | TBD: Toxicology section to provide an ability to Upload files (up to XX MB size) related to Toxicology results (Toxicology results file) | so that | DREs can attach Toxicology results directly to the evaluation and have online access to it.
THEME: | DREData 2.0 TOXICOLOGY ACCURACY
102 | 60 |  |  | NHTSA | EPIC | Audits on Evaluation Edits | As a(n) | NC/NTRC/SC/RC/AC/DRE | I want | the results of the Toxicology Report to be used to gauge the accuracy of the DRE’s initial evaluation. The accuracy score for the DRE to be calculated against the following criteria: - Scoring is zero-sum, and is calculated as 100% if the [opinion = the toxicology report] or if the [opinion is 1 less than the toxicology report]. All other combinations are scored as 0%. Scenarios are listed below : 1) A DRE records his Opinion of 2 Drugs (A & B), 2 Drugs are found (A & B): 100% 2) A DRE records his Opinion of 2 Drugs (A & B), 1 Drug is found (A): 100% 3) A DRE records his Opinion of 1 Drug (A), 0 Drugs found: 0% 4) A DRE records his Opinion of 3 Drugs (A, B & C), 1 drug is found (A): 0% 5) A DRE records his Opinion of 2 Drugs (A & B), 2 different drugs are found (C & D): 0% 6) A DRE records his Opinion of 2 Drugs (A & B), 2 Drugs found (A & D): 100% | so that | coordinators can track the accuracy of the toxicology results. | - If Plead Guilty checkbox is checked, this shall not be counted against DRE accuracy rate on View DRE Opinion and Toxicology Results Match Report. Where shall we capture Plead Guilty info? On Tox page?
THEME: | DREData 2.0 REPORTS
103 | 0 | TBD |  | NHTSA | EPIC | Reports Tab | As a(n) | NC/NTRC/SC/RC/AC/DRE | I want | the REPORTS tab to display the following information: - ALL REPORTS Subtab --- [See All Reports EPIC] - AD-HOC REPORTS Subtab --- [See AD-HOC Reports EPIC] - CANNED REPORTS Subtab --- [See CANNED Reports EPIC] | so that | I can successfully run any type of reports. | Need to know more about ADHOC reports
THEME: | DREData 2.0 MY ACCOUNT
116 | 120 |  |  | NHTSA | EPIC | My Account Tab | As a(n) | National Coordinator | I want | the MY ACCOUNT tab to display the following information: - MY PROFILE --- [See My Profile EPIC] - MY CERTIFICATIONS --- [See My Certifications EPIC] - CONTACT SC --- [See Contact SC EPIC] - ALERTS --- [See Alerts Theme] | so that | I can successfully manage my user account information and certifications.
117 |  | included in 116 |  | NHTSA | EPIC | My Profile Subtab | As a(n) | NC/NTRC/SC/RC/AC/DRE | I want | to have the following fields on the My Account page: - User Role - Additional Policies(s) - Agency - First Name - Last Name - Email* - [editable] - IACP (number)* - Secret questions to reset permanent password (TBD] [editable] - Current Password [editable] - New Password [editable] - Confirm New Password [editable] - Save [button] | so that | I can successfully manage my user account information.
THEME: | DREData 2.0 ADMIN / MANAGEMENT
121 |  | See below breakdown |  | NHTSA | EPIC | Admin (Management) Tab | As a(n) | NC/NTRC/SC/RC/AC | I want | the ADMIN (MANAGEMENT) tab to display the following information: - MANAGE USERS/OFFICERS --- [See Manage Officers EPIC] - CERTIFICATIONS --- [See Certifications EPIC] - REGIONS/AGENCIES --- [See Regions/Agencies EPIC] | so that | I can successfully manage other users and Regions/Agencies.
THEME: | DREData 2.0 HELP
127 | 1.5 |  |  | NHTSA | EPIC | NC Help Tab | As a(n) | NC/NTRC/SC/RC/AC/DRE | I want | the HELP tab to display requested by NHTSA information | so that | users can have a quick access to documentation.
THEME: | DREData 2.0 EMAIL NOTIFICATIONS
128 | 12 |  |  | NHTSA | EPIC | Email Notifications | As a(n) | NC/NTRC/SC/RC/AC/DRE | I want | TBD | so that | the users will get the email Notification every time ..... | Need the list of all notifications
THEME: | DREData 2.0 DATA MIGRATION FROM THIRD PARTY VENDORS
129 | 0 | TBD |  | NHTSA | EPIC | NC Help Tab | As a(n) | DRE System Owner | I want | the DRE data from States that are not using current DRE to be Migrated into DREData 2.0 database: MIGRATION: - All the legacy data currently in the DREData application to be required to be migrated into the new database. The new application to require a new data model to capture the new information, support the expanded roles and permissions, provide users reporting capabilities, and accurately present legacy records. - The DREData 2.0 web application to be a National Database for recording DRE Information. But because not all states or localities will leverage the system there is a business need to ingest and publish state information from non-DREData 2.0 systems. - States not using the DREData 2.0 web application to be required to provide their information in a to be defined .csv file - The .csv file must contain all of the DREData 2.0 required fields to be uploaded - Only a Site Administrator will have the ability to upload a state’s .csv file into the system. | so that | NHTSA can maintain DRE data integrity. | Need details
130 | 0 | TBD |  | NHTSA | EPIC | NC Help Tab | As a(n) | DRE System Owner | I want | the DRE data from States that are not using current DRE to be Published into DREData 2.0 database: PUBLISHING: - the data needs to be published and integrated with the all other State's DRE data. | so that | NHTSA data from all States available to DREData users. | Need details
THEME: | TECHNICAL DETAILS
131 | 240 |  |  | NHTSA | Epic |  | As a(n) |  | I want to | Application | so that
132 | 60 |  |  | NHTSA | Story |  | As a(n) |  | I want to | Creation of Data Model | so that
133 | 24 |  |  | NHTSA | Story |  | As a(n) |  | I want to | Application Controllers | so that
134 |  | included in 133 |  | NHTSA | Story |  | As a(n) |  | I want to | Application Views (Covered by above) | so that
135 | 120 |  |  | NHTSA | Story |  | As a(n) |  | I want to | Automated tests | so that
136 | 120 |  |  | NHTSA | Story |  | As a(n) |  | I want to | Application services (notifications, s3, search, queues, aws, etc...) | so that
THEME: | ADDITIONAL REQUESTS - TBD
143 |  |  |  | NHTSA | Epic |  |  | System Owner (Bill) | I want to | Email from Bill on 01/18/2017: At a security meeting yesterday, we were advised that the State DRE Coordinators might need to deactivate the accounts of users that have no activity in a 30 day period. To require the coordinators to have to manually go into the system to deactivate the account would devastate the process and would be catastrophic to the program. In the new system, would there be a way for the system itself to deactivate users and then, when users uses the appropriate access tools, could the system easily re-activate their account? TBD Details: Hi Bill, Yes, we can build the system so it will auto-deactivate user accounts, but we would need to get more details: 1. What do we exactly mean by no activity for 30 days. Does this mean the user did not log in within 30 day period? Or the user did not enter any data? 2. Also, are we going to apply this de-activation rule to all user roles: NC, SC, RC, DRE, DRE-INS, Basic User? 3. If SC do not want to be involved in reactivation process, then what will be the business rule for the system to re-activate the account? If user initiates the re-activation request, what does the system need to check in order to approve there request and make an account active again? The system can be build to handle anything, we just need to know if this is a high priority request and the details I have described above. If needed, we can have a conference call to discuss all these details. | so that
THEME: | DREData 2.0 SELF-REGISTRATION
144 | ? |  |  | NHTSA | EPIC | Self-Registration | As a(n) | DRE System Owner | I want | 1. The system to allow the users to perform self-registration for Basic User role, to authenticate, verify and approve registration for white-listed email domain automatically. 2. The Agency State Coordinator to grant policies or update user roles for registered Basic Users. | so that | all users with whitelisted email domains can register themselves in the system and Coordinators can add additional CRUD, R/A rights/policies. | Requested by Bill on 02/07/2017
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that
|  |  |  | NHTSA |  |  | As a(n) |  | I want to |  | so that

## RolesPermissionsPolicies
EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE | EXAMPLE
TABLE 1: User Roles/Permissions (default permissions)
Role + Perm | Read | Read What? | Create | Create What? | Update | Update What? | Approve | Approve What? | Reject | Reject What? | Submit | Submit What | Delete | Delete What?
NC | X | Any |  |  | X | Any | [6 empty] | X | Any
NTRC | X | NHTSA Region |  |  | X | NHTSA Region | [6 empty] | X | NHTSA Region
SC | X | State |  |  | X | State | X | State | X | State |  |  | X | State
RC | X | State |  |  |  |  | X | Region | X | Region
AC | X | Agency |  |  |  |  | X | Agency | X | Agency
DRE | X | Self | X | Self | X | Self |  |  |  |  | X | Self
TL (tox. lab user) |  |  |  |  | X (only Tox) | State
BU
TABLE 2: User Roles/Permissions + Additional Policies
(Role & Perm ) + Policy | Read | Read What? | Create | Create What? | Update | Update What? | Approve | Approve What? | Reject | Reject What? | Submit | Submit What
NR Policy
NC + NR | X | Any |  |  | X | Any | [6 empty] | X | Any
NTRC + NR | X | Any |  |  | X | NHTSA Region | [6 empty] | X | NHTSA Region
SC + NR | X | Any |  |  | X | State | X | State | X | State |  |  | X | State
RC + NR | X | Any |  |  |  |  | X | Region | X | Region
AC + NR | X | Any |  |  |  |  | X | Agency | X | Agency
DRE + NR | X | Any | X | Self | X | Self |  |  |  |  | X | Self
BU + NR | X | Any | NR is the only additional policy allowed on the Basic User role
DRE Policy
NC + DRE | X | Any | X | Self | X | Any |  |  |  |  | X | Self | X | Any
NTRC + DRE | X | NHTSA Region | X | Self | X | NHTSA Region |  |  |  |  | X | Self | X | NHTSA Region
SC + DRE | X | State | X | Self | X | State | X | State | X | State | X | Self | X | State
RC + DRE | X | State | X | Self | X | Self | X | Region | X | Region | X | Self
AC + DRE | X | Agency | X | Self | X | Self | X | Agency | X | Agency | X | Self
DRE + DRE | X | Self | X | Self | X | Self |  |  |  |  | X | Self
DRE-INS Policy
NC + DRE-INS | X | Any |  |  | X | Any | X | All | X | All |  |  | X | Any
NTRC + DRE-INS | X | NHTSA Region |  |  | X | NHTSA Region | X | NHTSA Region | X | NHTSA Region |  |  | X | NHTSA Region
SC + DRE-INS | X | State |  |  | X | State | X | State | X | State |  |  | X | State
RC + DRE-INS | X | State |  |  |  |  | X | State | X | State
AC + DRE-INS | X | State |  |  |  |  | X | State | X | State
DRE + DRE-INS | X | State | X | Self | X | Self | X | State | X | State | X | Self
NR and DRE Policy
NC + NR + DRE | X | Any | X | Self | X | Any |  |  |  |  | X | Self | X | Any
NTRC + NR + DRE | X | Any | X | Self | X | NHTSA Region |  |  |  |  | X | Self | X | NHTSA Region
SC + NR + DRE | X | Any | X | Self | X | State | X | State | X | State | X | Self | X | State
RC + NR + DRE | X | Any | X | Self | X | Self | X | Region | X | Region | X | Self
AC + NR + DRE | X | Any | X | Self | X | Self | X | Agency | X | Agency | X | Self
DRE + NR + DRE | X: X; Any: Any; X: X; Self: Self; X: X; State: Self; X: X; Self: Self
DRE-INS and DRE Policy
NC + DRE-INS + DRE | X | Any | X | Self | X | Any | X | All | X | All | X | Self | X | Any
NTRC + DRE-INS + DRE | X | NHTSA Region | X | Self | X | NHTSA Region | X | NHTSA Region | X | NHTSA Region | X | Self | X | NHTSA Region
SC + DRE-INS + DRE | X | State | X | Self | X | State | X | State | X | State | X | Self | X | State
RC + DRE-INS + DRE | X | State | X | Self | X | Self | X | State | X | State | X | Self
AC + DRE-INS + DRE | X | State | X | Self | X | Self | X | State | X | State | X | Self
DRE + DRE-INS + DRE | X | State | X | Self | X | Self | X | State | X | State | X | Self
DRE-INS and NR Policy
NC + DRE-INS + NR | X | Any |  |  | X | Any | X | All | X | All |  |  | X | Any
NTRC + DRE-INS + NR | X | Any |  |  | X | NHTSA Region | X | NHTSA Region | X | NHTSA Region |  |  | X | NHTSA Region
SC + DRE-INS + NR | X | Any |  |  | X | State | X | State | X | State |  |  | X | State
RC + DRE-INS + NR | X: X; Any: Any; X: X; All: State; X: X; All: State
AC + DRE-INS + NR | X: X; Any: Any; X: X; All: State; X: X; All: State
DRE + DRE-INS + NR | X | Any | X | Self | X | Self | X | State | X | State | X | Self
DRE-INS and DRE and NR Policy
NC + DRE-INS + DRE + NR | X | Any | X | Self | X | Any | X | All | X | All | X | Self | X | Any
NTRC + DRE-INS + DRE + NR | X | Any | X | Self | X | NHTSA Region | X | NHTSA Region | X | NHTSA Region | X | Self | X | NHTSA Region
SC + DRE-INS + DRE + NR | X | Any | X | Self | X | State | X | State | X | State | X | Self | X | State
RC + DRE-INS + DRE + NR | X | Any | X | Self | X | Self | X | State | X | State | X | Self
AC + DRE-INS + DRE + NR | X | Any | X | Self | X | Self | X | State | X | State | X | Self
DRE + DRE-INS + DRE + NR | X | Any | X | Self | X | Self | X | State | X | State | X | Self