## doc.info
Review
Defect Analysis
Project Name:
Approvals and Authorizations
Ver. No. | Ver. Date | Prepared By | Reviewed By | Review Date | Approved By | Affected Section & Summary of Change
1 |  | Rohini | Vamsi |  | Vamsi | Initial Version
[Template Version History (not to be modified by project teams)]
Ver. No. | Ver. Date | Prepared By | Reviewed By | Review Date | Approved By | Affected Section & Summary of Change | PIF No.
1 | 2012-06-06 | Padmaja | SEPG | 18/06/2012 | SEPG | Initial Version | NA

## Review Defect Chart
Review Defects Analysis
Analysis
Actions

## Review Defect Analysis data
Review Defect Analysis
S.no | Work Product | Subject (source) | Type of Defect (category) | Remarks
1 | PMP Plan | QMS | Tailoring approval | tailoring was not submitted to CPG and not approved
2 | BRS | Requirement | Incomplete Requirements | Solution Constraints not updated
4 | SRS | Requirement | Incomplete Requirements | capacity Requirements not updated
5 | SRS | Requirement | Incomplete Requirements | Portability not filled
6 | SRS | Requirement | Incomplete Requirements | Security Not updated
7 | SRS | Requirement | Incomplete Requirements | Constraints and Assumptions not filled
8 | SRS | Requirement | Incomplete Requirements | Off the shelf
9 | HLD | Design | Missing Design | RTM Not Updated for the Design
12 | HLD | Planning | Incomplete | MedfileID Not added
13 | HLD | Design | Incomplete Design | System Details/ components not updated
14 | HLD | Design | Incomplete Design | Intergration startgey not to be updated
15 | HLD | Design | Incomplete Design | Compnent type not update
16 | HLD | Design | Incomplete Design | Schedules not refered
17 | LLD | Design | Incomplete Design | Methods of the packages where not explained , there is no need of SDLC Method
18 | Code | Coding | Logic Defects | Naming conventions for connectionname is correct.
19 | Code | Coding | Logic Defects | Properties of DataFlowTask is mentioned
20 | Code | Coding | Logic Defects | File path has been assigned to the ConnectionString property
21 | Code | Coding | Logic Defects | Naming conventions for connectionname is correct
22 | Code | Coding | Logic Defects | variables are reflecting according to standards
23 | Code | Coding | Logic Defects | Foreach Loop Container there sholud be same file type.
24 | Code | Coding | Logic Defects | property DefaultbufferMaxRows is correct.
25 | Code | Coding | Logic Defects | Error log entry is correct
26 | Code | Coding | Logic Defects | All Dimesnions are in same sorted order
27 | Code | Coding | Logic Defects | required columns in queries are correct
28 | Code | Coding | Logic Defects | Flat File Data Retain nulls as nulls is correct.
29 | Code | Coding | Logic Defects | DefaultbufferMaxRows is correct
30 | Code | Coding | Logic Defects | Values in variables correct
31 | Code | Coding | Logic Defects | Merge Join is correct
32 | Code | Coding | Logic Defects | RequiredColoumns
33 | Code | Coding | Logic Defects | Transaction option for data flow tasks
34 | Code | Coding | Incomplete | ETLStatus is updated
35 | Code | Coding | Logic Defects | Properties expected result is done.
36 | Code | Coding | Logic Defects | Properties is not mentioned correctly
37 | Code | Coding | Logic Defects | Relations is not mentioned correctly
38 | Code | Coding | Logic Defects | Dimension Usage is correct.
39 | Code | Coding | Logic Defects | Partitions are created appropriately for better performance
40 | Code | Coding | Logic Defects | Properties is mentioned correctly
41 | Code | Coding | Logic Defects | Relations is mentioned correctly
42 | Code | Coding | Logic Defects | Transaction option for data flow tasks is updated
43 | Code | Coding | Logic Defects | Values in variables are mentioned
44 | Code | Coding | Logic Defects | Error log entry is correct
45 | Code | Coding | Logic Defects | Flat File Data Retain nulls as nulls
46 | Code | Coding | Logic Defects | DefaultbufferMaxRows are mentioned
47 | Code | Coding | Logic Defects | Flat File Data Retain nulls as nulls
48 | Code | Coding | Logic Defects | Flat File Data Retain nulls as nulls
49 | Code | Coding | Logic Defects | Partitions should be created appropriately for better performance
50 | Code | Coding | Logic Defects | Partitions should be created appropriately for better performance
51 | Code | Coding | Logic Defects | Dimension usage(Relations between dimensions and facts in cube) should be established correctly
52 | Code | Coding | Logic Defects | Properties is not mentioned correctly
53 | Code | Coding | Logic Defects | Relations is not mentioned correctly

## Test Defect Chart
Test Defect Anlaysis
Analysis
Actions

## Test Defect Analysis Data
Test Defect Analysis
S.no | Work Product | Subject (source) | Type of Defect (category) | Remarks | Module
1 | UnitTesting | Coding | Naming conventions | As developers are using the existing templates, they need to customise the templates according to requirements | DimENodeBLoad
2 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | DimENodeBLoad
3 | UnitTesting | Coding | Syntax/Semantic Errors in Coding | As developers are using the existing templates, they need to customise the templates according to requirements | DimCNumLoad
4 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | DimCNumLoad
5 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | DimPLMNcNumLoad
6 | UnitTesting | Coding | Syntax/Semantic Errors in Coding | Developers need to know the coding standards | DimcNumCause
7 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | DimcNumCause
8 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | DimDLlayer
9 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | DimDLlayer
10 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | DimCSFBIndicator
11 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | DimCSFBIndicator
12 | UnitTesting | Coding | Syntax/Semantic Errors in Coding | Developers need to know the coding standards | FactQHourlycNum
13 | UnitTesting | Coding | Logic Defects |  | FactQHourlycNum
14 | UnitTesting | Coding | Logic Defects |  | FactQHourlycNumQCI
15 | UnitTesting | Coding | Syntax/Semantic Errors in Coding | Developers need to know the coding standards | FactQHourlycNumQCI
16 | UnitTesting | Coding | Technology Issue |  | FactQhourlycNumEstabCause
17 | UnitTesting | Coding | Syntax/Semantic Errors in Coding | Developers need to know the coding standards | FactQhourlycNumEstabCauseQCI
18 | UnitTesting | Coding | Syntax/Semantic Errors in Coding | Developers need to know the coding standards | FactQhourlycNumEstabCauseQCI
19 | UnitTesting | Coding | Syntax/Semantic Errors in Coding | Developers need to know the coding standards | FactQhourlycNumscID
20 | UnitTesting | Coding | Syntax/Semantic Errors in Coding | Developers need to know the coding standards | FactQHourlycNumCalc
21 | UnitTesting | Coding | Technology Issue | Developers have to establish the connections by deleting the old connections | FactQHourlycNumCSFBIndicator
22 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactQHourlycNumCSFBIndicatorSIBOwn
23 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactQHourlycNumDLLayer
24 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactQHourlycNumDLLayerCodeword
25 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactQHourlycNumDLLayercodewordStatus
26 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactQHourlycNumEstabCauseCalc
27 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactHourlycNumHOCause
28 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactHourlycNumLevel
29 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactHourlycNumNeighborCell
30 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactHourlycNumQCICalc
31 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactHourlycNumReEstabCause
32 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactHourlycNumTargetEarfcnDl
33 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactHourlycNumtcIDHOCause
34 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactDailycNumtcIDHOCauseCalc
35 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactDailycNumtcIDStep
36 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactDailyEnodeB
37 | UnitTesting | Coding | Syntax/Semantic Errors in Coding | Developers need to know the coding standards | FactDailyEnodeBCalc
38 | UnitTesting | Coding | Logic Defects | As developers are using the existing templates, they need to customise the templates according to requirements | FactDailyPLMNcNum
39 | UnitTesting | Coding | Logic Defects | Dimension usage(Relations between dimensions and facts in cube) should be established correctly | SamsungLTEQhourlycube
40 | UnitTesting | Coding | Logic Defects | Relations should be established appropriately between the dimensions and related facts(In DSV) | SamsungLTEhourlycube
41 | UnitTesting | Coding | Logic Defects | Partitions should be created appropriately for better performance | SamsungLTEDailycube
43 | SystemTesting | Coding | Syntax/Semantic Errors in Coding | Checking for Naming conventions | DimCNumLoad
44 | SystemTesting | Coding | Logic Defects | Query resultset should be same as destination data | FactQHourlycNum
45 | SystemTesting | Coding | Logic Defects | Both source row count and destination row count are same | FactQHourlycNumDLLayerCodeword
46 | SystemTesting | Coding | Syntax/Semantic Errors in Coding | Checking for Naming conventions | FactQHourlycNumHOCause
47 | SystemTesting | Coding | Logic Defects | Checking for Naming conventions | FactHourlycNum
48 | SystemTesting | Coding | Logic Defects | Compare this data with source data | FactHourlycNumCSFBIndicatorSIBOwn
49 | SystemTesting | Coding | Syntax/Semantic Errors in Coding | Check the source and destination connection strings | FactHourlycNumDLLayerCodewordStatus
50 | SystemTesting | Coding | Logic Defects | Query resultset should be same as destination data | FactDailycNum
51 | SystemTesting | Coding | Logic Defects | Both source row count and destination row count are same | FactDailycNumDLLayerCodeword
52 | SystemTesting | Coding | Syntax/Semantic Errors in Coding | Checking for Naming conventions | FactDailycNumHOCause