## Revision Log
Project Name | Analytics Data Warehouse
Document Update History
Doc.Ver.No. | Date | Summary of Updates | Updated By | Approved by | Approved on
Template Revision History
Version | Date | Summary of Changes | Approved By
1 | 2019-05-31 | Initial Template revision | CPG
1 | 2020-02-14 | Added Effort Analysis and updated Story Point Estimates tab | C. Shacklett
1.1 | 2020-04-24 | Updated Velocity Analysis and Effort Analysis | C. Shacklett

## Considerations
Estimation Considerations
ASSUMPTIONS
Based on the assumption that the associate is proficient in the concerned technologies.
CONSTRAINTS & DEPENDENCIES
This is specific to custom development activities and is not dependent on any specific Software Vendor. All the team should be aware of Agile Methodology.
RISKS
This estimation model might not apply to traditional implementation models.
SKILLS & EXPERIENCE OF RESOURCES
Any programming language.
HOW TO ASSESS STORY POINTS
1. Identify base stories. 2. Talk through the requirements of the story. 3. Discuss and jot down things you want to remember when implementing this story. 4. Some of these questions team ask themselves when they start sizing. • Design: What will we have to learn before we can start work on this story? • Coding: How much code will need to be written for this story? Have we written similar code before? • Unit Testing: Will any special setup (e.g., mock objects) be required to unit test this story? • Acceptance Testing: How much work is involved in helping the customer to automate the acceptance tests for this story? • Integration Points: Does this story have external dependencies? • Expertise: Does anyone of us have done similar story before? 5. Find some point of relative comparison. 6. Reach a consensus among entire team present as to the size of the story as per definition of done. 7. Validate that your estimates are internally consistent among stories as you go along. 8. Periodically ensure that all of the 1′s are about the same, all of the 2′s match, etc.

## Story Point Estimates
Story Point Estimation - Poker Planning Method
| Release Name | Backend Dev
Ticket Rolled Over | Sprint 1 | Dev 1 | Dev 2 | Dev 3 | Dev 4 |  | Estimated Story Point | Actual Story Point | Estimated Effort | Actual Effort
[11 empty] | Story Points | Time Bucket
[11 empty] | 1 | <1 days
[11 empty] | 2 | 1 - 2 days
[11 empty] | 3 | 3 - 4 days
[11 empty] | 5 | 5 - 7 days
[11 empty] | 8 | 8 - 10 days
[11 empty] | 13 | 11 - 20 days
[11 empty] | 21 | 21 - 30 days
[11 empty] | 34 | >30 days
Total
Ticket Rolled Over | Sprint 2 | Dev 1 | Dev 2 | Dev 3 | Dev 4 |  | Estimated Story Point | Actual Story Point | Estimated Effort | Actual Effort
Total
Ticket Rolled Over | Sprint 3 | Dev 1 | Dev 2 | Dev 3 | Dev 4 |  | Estimated Story Point | Actual Story Point | Estimated Effort | Actual Effort
Total

## Velocity Analysis
Velocity Analysis
Sprint Name | Number of People | Actual Story Points/Velocity (Manually) | Number of working hours in Sprint Juan | Number of working hours in Sprint Justin | Number of working hours in Sprint Joe | Number of working hours in Sprint Jonathan | Number of working hours in Sprint Ben | Number of working hours in Sprint Angel | Number of working hours in Sprint Claude | Total Work Hours | Points per Business Hour per Team | Average Analysis per Team | Target Sprint Velocity per Team | Date of analysis
Sprint | [9 empty] | 0 | 0 | 0
Sprint | [9 empty] | 0 | 0 | 0 | 0
Sprint | [9 empty] | 0 | 0 | 0 | 0
Sprint | [9 empty] | 0 | 0 | 0 | 0
Sprint | [9 empty] | 0 | 0 | 0 | 0
Sprint | [9 empty] | 0 | 0 | 0 | 0
Sprint | [9 empty] | 0 | 0 | 0 | 0
Sprint | [9 empty] | 0 | 0 | 0 | 0
Sprint | [9 empty] | 0 | 0 | 0 | 0
Sprint | [9 empty] | 0 | 0 | 0 | 0
Sprint | [9 empty] | 0 | 0 | 0 | 0
Sprint | [9 empty] | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0

## Effort Analysis
Estimation Analysis Date (every 4-6 sprints) 02/14/2020
Sprint | Ticket # | Estimated Story Point | Actual Story Point | Estimated Effort | Actual Effort |  | Story Points | Current Time Bucket | Adjusted Time Bucket after analysis
[7 empty] | 1 | <1 days | <=4 days
[7 empty] | 2 | 1 - 2 days | 5 - 7 days
[7 empty] | 3 | 3 - 4 days | 8 - 10 days
[7 empty] | 5 | 5 - 7 days | 11 - 14 days
[7 empty] | 8 | 8 - 10 days | 15 - 19 days
[7 empty] | 13 | 11 - 20 days | 20 - 25 days
[7 empty] | 21 | 21 - 30 days | 26 - 31 days
[7 empty] | 34 | >30 days | >31